## Gantt Chart
| Planned |  |  | Actual
Task (User Input) | Start Date (User Input) | End Date | Duration (User Input) | Start Date (User Input) | End Date (User Input) | Duration | Task Status (User Input) | time axis 2022-01-01 to 2022-07-01
Task 1 | 2022-01-01 | 2022-02-18 | 30 | 2020-01-05 | 2020-01-22 | 13 | Completed | bar: 2022-01-01 to 2022-02-18
[8 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Task 2 | 2022-01-12 | 2022-02-02 | 15 | 2020-01-14 | 2020-02-03 | 15 | Completed | bar: 2022-01-12 to 2022-02-02
[19 empty] | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A | A
Task 3 | 2022-01-18 | 2022-01-28 | 8 | 2022-02-14 | 2022-03-31 | 34 | Pending | bar: 2022-01-18 to 2022-01-28
Task 4 | 2022-01-30 | 2022-02-07 | 6 |  |  | 0 | Pending | bar: 2022-01-30 to 2022-02-07
Task 5 | 2022-02-05 | 2022-02-21 | 11 |  |  | 0 | Pending | bar: 2022-02-05 to 2022-02-21
Task 6 | 2022-02-22 | 2022-03-14 | 14 |  |  | 0 | Pending | bar: 2022-02-22 to 2022-03-14
Task 7 | 2022-03-13 | 2022-04-14 | 23 |  |  | 0 | Pending | bar: 2022-03-13 to 2022-04-14
Task 8 | 2022-04-10 | 2022-04-18 | 6 |  |  | 0 | Pending | bar: 2022-04-10 to 2022-04-18
Task 9 | 2022-04-29 | 2022-05-11 | 8 | 2022-04-29 | 2022-05-11 | 0 | Pending | bar: 2022-04-29 to 2022-05-11
Task 10 | 2022-04-29 | 2022-05-09 | 6 |  |  | 0 | Pending | bar: 2022-04-29 to 2022-05-09
Task 10 | 2022-04-29 | 2022-05-09 | 6 | 0 | 0 | -5 | Pending | bar: 2022-04-29 to 2022-05-09
2. Completed Timeline Breakup
Delayed
Actual
Extended
1. Overall Task Status
Pending
In Progress
Completed

## Holidays
# Please add holidays dates to exclude days from project ending date calculation.
Date | Day | Holiday
2022-01-01 | Wednesday | New Year’s Day
2022-01-02 | Friday | Good Friday
2022-01-03 | Monday | Easter Monday
2022-01-04 | Friday | Early May bank holiday (VE day)
2022-01-05 | Monday | Spring bank holiday
2022-01-06 | Monday | Summer bank holiday
2022-01-07 | Friday | Christmas Day
2022-01-08 | Monday | Boxing Day (substitute day)
2022-04-04