## MATRIX
APQP - Matrix | [9 empty] | DOC NO :- NPD/DI/R/05A REV NO :- 00 DATE :- 21.09.2020
PART NAME : APQP MATRIX |  | PART NO : 29328249 | [7 empty] | CSUTOMER : BIPL
# | Activity | Developments |  |  |  |  | Responsibilities and interactions
|  | New design | Same family | New RM | Existing RM | CFT Discussion | Mkt. | NPD | QA | Mfg | Tool | Main | HR | Pur
1 | ENQUIRY REGISTER UPDATION | X | X |  | X | X |  | O
2 | PRODUCT INFORMATION DATA | X | X |  | X |  |  | O | O | O | O
3 | MANUFACTURING FEASIBILITY REVIEW | X | X |  | X | X |  | O | O | O | O | O | O | O
4 | RISK ANALYSIS | X | X |  | X | X |  | O | O | O | O
5 | QUOTE PREPARATION & SUBMISSION | X | X |  | X |  |  | O |  | O
6 | CUSTOMER SPECIFIC REQUIREMENTS | X | X |  | X | X | O | O | O | O | O | O | O | O
7 | IDENTIFICATION OF SPECIAL CHARACTERISTICS | X | X |  | X |  | O | O
8 | IDENTIFICATION GAUGE & TESTING EQUIPEMENT | X | X |  | X | X | O | O
9 | THINGS GONE WRONG & THINGS GONE RIGHT | X | X |  | X | X |  | O | O | O
10 | MANAGEMENT REVIEW & SUPPORT MEETING I | X | X |  | X | X |  | O |  | O | O
11 | PROCESS FLOW DIAGRAM | X | X |  | X | X | O | O |  | O
12 | Process FMEA | X | X |  | X | X |  | O | O
13 | FINALIZATION OF SPECIAL CHARACTERISTICS | X | X |  | X | X | O | O | O | O | O | O | O | O
14 | GAUGE DESIGN & DEVELOPMENT | X | X |  | X | X |  | O | O | O | O
15 | FINALIZATION OF GAUGE & TESTING & EQUIPEMENT | X | X |  | X | X |  |  |  |  | O
16 | PROCUREMENT OF GAUGE & TESTING EQUIPEMENT | X | X |  | X | X | O | O | O | O
17 | TOOL DESIGN | X | X |  | X | X |  | O | O | O
18 | TOOL MANUFACTURING | X | X |  | X | X | O | O |  | O
19 | TOOL INSPECTION & ASSEMBLY | X | X |  | X | X |  | O | O | O
20 | TOOL TRIAL &VALIDATION | X | X |  | X | X |  | O | O | O
21 | DEVELOPMENT OF SUBCONTRACTOR PROCESS | X | X |  | X | X | O | O | O | O | O | O | O | O
22 | MISTAKE PROOFING | X | X |  | X | X | O | O |  | O
23 | PRE LAUNCH CONTROL PLAN | X | X |  | X |  |  | O | O
24 | WORK INSTRUCTIONS | X | X |  | X |  |  | O | O
25 | PACKING SPECIFICATION PREPARATION | X | X |  | X |  |  | O | O
26 | PACKING SIGN OFF APPROVAL | X | X |  | X | X |  | O | O
27 | SIR SAMPLE SUBMISSION | X | X |  | X | X |  | O
28 | SIR SAMPLE APPROVAL | X | X |  | X | X | O | O | O | O | O | O | O | O
29 | MANAGEMENT REVIEW & SUPPORT MEETING II | X | X |  | X | X | O | O |  | O
30 | MSA STUDY
31 | SPC STUDY
32 | GAUGE R & R
33 | PTR SIGN OFF
34 | PPAP PREPARATION
35 | PPAP SUBMISSION
36 | MANAGEMENT REVIEW & SUPPORT MEETING III
37 | PTR sign off | X | X |  | X | X | O | O | O | O | O
38 | Safe launch 1 | X | X |  | X | X |  | O | O | O
39 | Safe launch 2 | X | X |  | X | X |  | O | O | O
40 | Safe launch 3 | X | X |  | X | X |  | O | O | O
41 | Safe launch sign off | X | X |  | X | X |  | O | O
42 | Management Review & Support V | X | X |  | X | X | O | O | O | O | O | O | O | O
X - Point to be implemented |  |  | Blank - Not applicable |  |  |  | O - Responsibility
PREPARED BY :- M.Bharathi

## Sheet1
` | Same family | VSSIPL initiated changes | CFT Discussion